## Work Items List 1.2
Item | Name / Description | Priority | Size estimate (S-M-L) | State | Target iteration(s) | Assigned To | Effort estimate left (hours) | Hours worked | Reference material
1 | Decide on the project's category and compose the usage scenario roughly. | High | S | Done | 1 | İbrahim | As a team, throughout the lifecycle of the project, we will follow "NoEstimates" movement, since it puts unnecessary pressure on team members and very hard to make sharp predictions. That's why, we find it pointless. Only a rough estimate will be done using t-shirt sizes as you can see in Size Estimate column. Hours worked and effort estimate left columns will be left empty because of these reasons. |  | No specified material
2 | Make Ready the first draft of the Vision Document according to the project definition. | High | M | Done | 1 | Rukiye-Sibel |  |  | Vision document
3 | Prepare a Glossary document which includes the jargon that will be in use throughout the project's lifecycle. | Low | S | Done | 1 | Rukiye |  |  | Glossary document
4 | Make researches to obtain Know-How in Test Driven Development | High | S | Done | 1 | Rukiye |  |  | No specified material
5 | Design a modular core architecture to realize use cases. | High | M | Done | 2 | Sibel |  |  | Architecture Notes
6 | Prepare Work Item List document (first draft) which includes the items to be done in each iteration (Items belong to closer iterations must be granular enough to realize). | High | M | Done | 1 | Sibel |  |  | Work Items List document
7 | Decide on the use cases that will be realized throughout the project and document them in Use Case artifact. (First Draft) | High | M | Done | 1 | Sibel-Rukiye |  |  | Use Case document
8 | Make plan for the Iteration 2. | High | S | Done | 1 | Sibel |  |  | Iteration 2 Plan
9 | Do forecasting session to discover the risks that may occur throughout the project and include them in Risk List. | Medium | M | Done | 1 | Rukiye-Sibel |  |  | Risk List document
10 | Prepare a plan for whole life-cycle of the project and include this plan in Project Plan artifact. | High | M | Done | 1 | Rukiye-Sibel |  |  | Project Plan document
11 | Elaborate and classify system requirements. Form a System Wide Requirements artifact with them. (First Draft) | High | M | Done | 1 | Rukiye-İbrahim |  |  | System Wide Requirements document
12 | Update Iteration 1 artifacts according to the feedbacks of Quality Team. | High | S | Done | 2 | Rukiye-İbrahim-Sibel |  |  | Second version of Iteration 1 artifacts (documents in previous rows).
13 | Update Iteration 2 artifacts according to the feedbacks of Quality Team. | High | S | Done | 2 | Rukiye-İbrahim-Sibel |  |  | Second version of Iteration 1 artifacts (documents in previous rows).
14 | Play Game Use Case Realization | High | L | In progress | 3 | İbrahim |  |  | Use Case document
15 | Prepare test cases for "Play Game" use case | High | M | Done | 2 | Rukiye |  |  | Test case list for "Play Game" use case
16 | Write test script for test cases written for the "Play Game" use case | High | S | Done | 2 | Rukiye |  |  | Script to run test cases for "Play Game" use case
17 | Collect and anayze the test logs for tests run on the "Play Game" use case. | High | M | In progress | 2 | Rukiye |  |  | Test Results Document for "Play Game" use case
18 | Change Settings Use Case Realization | High | M | In progress | 3 | İbrahim |  |  | Use Case document
19 | Prepare test cases for "Change Settings" use case | High | M | Done | 3 | Rukiye |  |  | Test case list for "Change Settings" use case
20 | Write test script for test cases written for the "Change Settings" use case | High | S | Done | 3 | Rukiye |  |  | Script to run test cases for "Change Settingse" use case
21 | Collect and anayze the test logs for tests run on the "Change Settings" use case. | High | M | In progress | 3 | Rukiye |  |  | Test Results Document for "Change Settings" use case
22 | Make Assessment for Iteration 2. | Medium | S | Done | 2 | Rukiye-İbrahim-Sibel |  |  | Iteration 2 plan document
23 | Make Assessment for Iteration 3 | Medium | S | In progress | 3 | Rukiye-İbrahim-Sibel |  |  | Iteration 3 plan document
24 | Make a roadmap and clarify the ambiguities to prepare the Iteration 2 artifacts. | Medium | S | In progress | 2 | Sibel |  |  | No specified material
25 | "Login" Use Case Realization (Will be refined). | Low | L | To Do | 4 | İbrahim |  |  | Use Case document
26 | Prepare test cases for "Login" use case | High | M | To Do | 4 | Rukiye |  |  | Use Case document
27 | Write test script for test cases written for the "Login" use case | High | S | To Do | 4 | Rukiye |  |  | Use Case document
28 | Collect and anayze the test logs for tests run on the "Login" use case. | High | M | To Do | 4 | Rukiye |  |  | Use Case document
29 | "Chat with Other Players" Use Case Realization (Will be refined). | Low | L | To Do | 5 | İbrahim |  |  | Use Case document
30 | Prepare test cases for "Chat with Other Players" use case | High | M | To Do | 5 | Rukiye |  |  | Use Case document
31 | Write test script for test cases written for the "Chat with Other Players" use case | High | S | To Do | 5 | Rukiye |  |  | Use Case document
32 | Collect and anayze the test logs for tests run on the "Chat with Other Players" use case. | High | M | To Do | 5 | Rukiye |  |  | Use Case document
33 | "Change Player Attributes" Use Case Realization (Will be refined). | Medium | L | To Do | 4 | İbrahim |  |  | Use Case document
34 | Prepare test cases for "Change Player Attributes" use case | High | M | To Do | 4 | Rukiye |  |  | Use Case document
35 | Write test script for test cases written for the "Change Player Attributes" use case | High | S | To Do | 4 | Rukiye |  |  | Use Case document
36 | Collect and anayze the test logs for tests run on the "Change Player Attributes" use case. | High | M | To Do | 3 | Rukiye |  |  | Use Case document
37 | "Watch Commercial to Gain Gems" Use Case Realization (Will be refined). | Low | L | To Do | 3 | İbrahim |  |  | Use Case document
38 | Prepare test cases for "Watch Commercial to Gain Gems" use case | High | M | To Do | 3 | Rukiye |  |  | Use Case document
39 | Write test script for test cases written for the "Watch Commercial to Gain Gems" use case | High | S | To Do | 3 | Rukiye |  |  | Use Case document
3 | Collect and anayze the test logs for tests run on the "Watch Commercial to Gain Gems" use case. | High | M | To Do | 3 | Rukiye |  |  | Use Case document
41 | "Join Competitions" Use Case Realization (Will be refined). | Low | L | To Do | 5 | İbrahim |  |  | Use Case document
42 | Prepare test cases for "Join Competitions" use case | High | M | Done | 5 | Rukiye |  |  | Use Case document
43 | Write test script for test cases written for the "Join Competitions" use case | High | S | To Do | 5 | Rukiye |  |  | Use Case document
44 | Collect and anayze the test logs for tests run on the "Join Competitions" use case. | High | M | To Do | 5 | Rukiye |  |  | Use Case document
45 | "Upgrade Account" Use Case Realization (Will be refined). | Low | L | To Do | 4 | İbrahim |  |  | Use Case document
46 | Prepare test cases for "Upgrade Account" use case | High | M | To Do | 4 | Rukiye |  |  | Use Case document
47 | Write test script for test cases written for the "Upgrade Account" use case | High | S | To Do | 4 | Rukiye |  |  | Use Case document
48 | Collect and anayze the test logs for tests run on the "Upgrade Account" use case. | High | M | To Do | 4 | Rukiye |  |  | Use Case document

## Revision History
Date | Version | Description | Author
2022-04-02 | 1.0 | Draft 1 | Scape from Mon
2022-04-02 | 1.1 | Iteration 2 size estimates and efforts added. | Scape from Mon
2022-04-29 | 1.2 | Iteration 3 size estimates and efforts added. | Scape from Mon