## Sheet1
Item | Name / Description | Priority | Size estimate (Points) | State | Target iteration | Assig-ned To | Effort estimate left (hours) | Hours worked | Reference material
1 | Produce Vision Document First Version | 1 | 2 | Resolved | 1 | Rukiye-Sibel | - | 15 | <Vision.doc>
2 | Produce Glossary Document First Version | 1 | 2 | Resolved | 1 | Rukiye-Sibel | - | 3 | <Glosorry.doc>
3 | Produce Vision Document Second Version | 1 | 2 | Verified | 2 | Sibel | - | 15 | <Vision.doc>
4 | Start implementation of "Play Game" Use Case | 1 | 20 | Open | 2 | İbrahim | - | - | <UC:Play Game>
5 | Start implementation of "Login" Use Case | 4 | 8 | Open | 6 | İbrahim | - | - | -
6 | Start implementation of "Chat with Other Players" Use Case | 4 | 25 | Open | 6 | İbrahim | - | - | -
7 | Start implementation of "Change Player Attributes" Use Case | 1 | 16 | Open | 2 | İbrahim | - | - | -
8 | Start implementation of "Watch Commercial to Gain Gems" Use Case | 2 | 15 | Open | 4 | İbrahim | - | - | -
9 | Start implementation of "Change Settings" Use Case | 1 | 10 | Open | 2 | İbrahim | - | - | -
10 | Start implementation of "Join Competitions" Use Case | 4 | 25 | Open | 6 | İbrahim | - | - | -
11 | Produce Risk List | 1 | 1 | Resolved | 1 | Sibel | - | - | <RiskList.doc>
12 | Produce Iteration 2 plan | 1 | 3 | Resolved | 1 | Sibel | - | - | <IterationPlan.doc>
13 | Produce Project Plan | 1 | 5 | Resolved | 1 | Sibel | - | - | <ProjectPlan.doc>
14 | Produce System-Wide Requirements Specification | 1 | 13 | Resolved | 1 | Rukiye | - | 15 | <System-Wide Requirements Specification.doc>
15 | Produce test cases for the use case "Play Game" | 1 | 17 | Open | 2 | Rukiye | - | - | <Test-Case.doc>
16 | Run test cases for the use case "Play Game" | 1 | 15 | Open | 2 | Rukiye | - | - | -
17 | Finalize the Vision | 3 | 4 | Open | 4 | Sibel | - | - | <Vision.doc>
18 | Finalize the System-Wide Requirements Specification | 3 | 4 | Open | 4 | Rukiye | - | - | <System-Wide Requirements Specification.doc>
19 | Finalize test cases for all use cases | 2 | 20 | Open | 4 | İbrahim | - | - | <Test-Case.doc>
20 | Design the core architecure | 1 | 20 | Open | 2 | İbrahim | - | - | -
21 | Fill the Assessment part of Iteration 2 plan | 2 | 2 | Open | 2 | Sibel | - | - | -