## Risks
Scape From Mon Risk List
Risk ID | Date Identified | Headline | Description | Type | Impact | Probability | Magnitude | Owner | Mitigation Strategy
1 | 2022-04-02 | Problem of Meeting Deadlines | For each iteration there is problem of not meeting the objectives because of low number of workers. E | D | 5 | 50% | 2.5 | Project Manager | Every team member work on multiple jobs at the same time to mitigate this risk.
2 | 2022-04-07 | Lack of Communication | Failure to communicate may cause employees to make the wrong assumptions, such as leaving other employees to pick up their work, when this task was not previously discussed between a team. | D | 3 | 20% | 0.6 | All team | Regular meetings are held within the team regarding the processes.
4 | 2022-04-07 | Project Requirements are not well defined | An inadequate understanding of the intended users and the context | D | 5 | 50% | 2.5 | Analyst | Regular meetings are held within the team regarding the processes.
5 | 2022-04-07 | Technical Difficulties | Hardware and Software Problems | D | 5 | 60% | 3 | Developers | Review and prioritize difficulties, eliminating those with lowest probability.
6 | 2022-04-08 | Poor User Experience | Collecting negative comments from the players | D | 5 | 80% | 4 | All team | At the initial version of the game, should be made some online surveys with the players.
Note on E2: Type = I (indirect) or D (direct)
Note on F2: Impact is a numerical value, usually between 1 and 5, that represents the impact to the project if the risk comes true. 5 is a HIGH IMPACT and 1 is LOW IMPACT.
Note on G2: Probability is the percentage chance that a risk will occur.
Note on H2: Magnitude is the result of the multiplication of Probability and Impact, providing a joint metric suitable for sorting.

## Revision History
Date | Version | Description | Author
2022-04-02 | 1.0 | Draft 1 | Scape From Mon
2022-04-08 | 1.1 | Version 1.1 | Scape From Mon