## Work Items List 1.0
Item | Name / Description | Priority | Size estimate (S-M-L) | State | Target iteration(s) | Assigned To | Effort estimate left (hours) | Hours worked | Reference material
1 | Decide on the project's category and compose the usage scenario roughly. | High | S | Done | 1 | İbrahim | As a team, throughout the lifecycle of the project, we will follow "NoEstimates" movement, since it puts unnecessary pressure on team members and very hard to make sharp predictions. That's why, we find it pointless. Only a rough estimate will be done using t-shirt sizes as you can see in Size Estimate column. Hours worked and effort estimate left columns will be left empty because of these reasons. |  | No specified material
2 | Make Ready the first draft of the Vision Document according to the project definition. | High | M | Done | 1 | Rukiye-Sibel |  |  | Vision document
3 | Prepare a Glossary document which includes the jargon that will be in use throughout the project's lifecycle. | Low | S | Done | 1 | Rukiye |  |  | Glossary document
4 | Make researches to obtain Know-How in Test Driven Development | High | S | Done | 1 | Rukiye |  |  | No specified material
5 | Design a modular core architecture to realize use cases. | High | M | In progress | 2022-01-02 | Sibel |  |  | Architecture Notes
6 | Prepare Work Item List document (first draft) which includes the items to be done in each iteration (Items belong to closer iterations must be granular enough to realize). | High | M | Done | 1 | Sibel |  |  | Work Items List document
7 | Decide on the use cases that will be realized throughout the project and document them in Use Case artifact. (First Draft) | High | M | Done | 1 | Sibel-Rukiye |  |  | Use Case document
8 | Make plan for the Iteration 2. | High | S | Done | 1 | Sibel |  |  | Iteration 2 Plan
9 | Do forecasting session to discover the risks that may occur throughout the project and include them in Risk List. | Medium | M | Done | 1 | Rukiye-Sibel |  |  | Risk List document
10 | Prepare a plan for whole life-cycle of the project and include this plan in Project Plan artifact. | High | M | Done | 1 | Rukiye-Sibel |  |  | Project Plan document
11 | Elaborate and classify system requirements. Form a System Wide Requirements artifact with them. (First Draft) | High | M | In progress | 1 | Rukiye-İbrahim |  |  | System Wide Requirements document
12 | Update Iteration 1 artifacts according to the feedbacks of Quality Team. | High | S | Done | 2 | Rukiye-İbrahim-Sibel |  |  | Second version of Iteration 1 artifacts (documents in previous rows).
13 | Play Game Use Case Realization
14 | Prepare test cases for "Play Game" use case | High | M | In progress | 2 | Rukiye |  |  | Test case list for "Play Game" use case
15 | Write test script for test cases written for the "Play Game" use case | High | S | To Do | 2 | Rukiye |  |  | Script to run test cases for "Play Game" use case
16 | Collect and anayze the test logs for tests run on the "Play Game" use case. | High | M | To Do | 2 | Rukiye |  |  | Test Results Document for "Play Game" use case
17 | Make Assessment for Iteration 2. | Medium | S | To Do | 2 | Rukiye-İbrahim-Sibel |  |  | Iteration 3 plan document
18 | Make a roadmap and clarify the ambiguities to prepare the Iteration 2 artifacts. | Medium | S | In progress | 2 | Sibel |  |  | No specified material
19 | "Login" Use Case Realization (Will be refined). | Low | L | To Do | 5 | Unassigned |  |  | To be defined
20 | "Chat with Other Players" Use Case Realization (Will be refined). | Low | L | To Do | 6 | Unassigned |  |  | To be defined
21 | "Change Player Attributes" Use Case Realization (Will be refined). | Medium | L | To Do | 3 | Unassigned |  |  | To be defined
22 | "Watch Commercial to Gain Gems" Use Case Realization ( Will be refined). | Low | L | To Do | 4 | Unassigned |  |  | To be defined
23 | "Change Settings" Use Case Realization (Will be refined). | Medium | L | To Do | 3 | Unassigned |  |  | To be defined
24 | "Join Competitions" Use Case Realization (Will be refined). | Low | L | To Do | 6 | Unassigned |  |  | To be defined
25 | "Upgrade Account" Use Case Realization (Will be refined). | Low | L | To Do | 5 | Unassigned |  |  | To be defined